## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-05-06 |  |  |  |  | May | [27 empty] | June
Scrolling Increment: | 1 | time axis 2024-05-07 to 2024-07-01
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-05-07 to 2024-07-01
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-06 | 3 | 2024-05-07: 2; 2024-05-08: 2
Task 2 | Milestone |  |  | 2024-05-11 | 1 | bar: 2024-05-11
Task 3 | Low Risk |  | 50% | 2024-05-03 | 10
Task 4 | Milestone |  |  | 2024-05-26 | 1 | bar: 2024-05-26
Task 5 | Med Risk |  | 10% | 2024-05-12 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-05-12 | 13
Task 2 | On Track |  | 50% | 2024-05-14 | 9
Task 3 | Low Risk |  | 33% | 2024-05-19 | 11
Task 4 | Milestone |  |  | 2024-05-21 | 1 | bar: 2024-05-21
Task 5 |  |  |  | 2024-05-22 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-05-21 | 4
Task 2 | Med Risk |  |  | 2024-05-24 | 14
Task 3 | On Track |  |  | 2024-06-08 | 6
Task 4 | Goal |  |  | 2024-06-12 | 3 | 2024-06-12: 2; 2024-06-13: 2; 2024-06-14: 2
Task 5 | Low Risk |  |  | 2024-05-12 | 19
TITLE 4
Task 1 |  |  |  | 2024-06-15 | 15
Task 2 |  |  |  | 2024-06-29 | 5
Task 3 | Milestone |  |  | 2024-08-10 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-05-06 |  |  |  |  | May | [27 empty] | June
Scrolling Increment: | 1 | time axis 2024-05-07 to 2024-07-01
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-06 | 3 | T: 2; W: 2
Task 2 | Milestone |  |  | 2024-05-11 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2024-05-03 | 10
Task 4 | Milestone |  |  | 2024-05-26 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2024-05-12 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-05-12 | 13
Task 2 | On Track |  | 50% | 2024-05-14 | 9
Task 3 | Low Risk |  | 33% | 2024-05-19 | 11
Task 4 | Milestone |  |  | 2024-05-21 | 1 | bar: T
Task 5 |  |  |  | 2024-05-22 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-05-21 | 4
Task 2 | Med Risk |  |  | 2024-05-24 | 14
Task 3 | On Track |  |  | 2024-06-08 | 6
Task 4 | Goal |  |  | 2024-06-12 | 3 | W: 2; T: 2; F: 2
Task 5 | Low Risk |  |  | 2024-05-12 | 19
TITLE 4
Task 1 |  |  |  | 2024-06-15 | 15
Task 2 |  |  |  | 2024-06-29 | 5
Task 3 | Milestone |  |  | 2024-08-10 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Cell |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead Artem Hrytsenko
Project Start Date: | 2024-02-22 |  |  |  |  | February | [13 empty] | March | [27 empty] | April
Scrolling Increment: | 0 | time axis 2024-02-22 to 2024-04-17
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-02-22 to 2024-04-17
Iteration 1
Finish First Iteration | Goal | Rhys, Terrence, Artem | 100% | 2024-02-22 | 18 | 2024-02-22: 2; 2024-02-23: 2; 2024-02-24: 2; 2024-02-25: 2; 2024-02-26: 2; 2024-02-27: 2; 2024-02-28: 2; 2024-02-29: 2; 2024-03-01: 2; 2024-03-02: 2; 2024-03-03: 2; 2024-03-04: 2; 2024-03-05: 2; 2024-03-06: 2; 2024-03-07: 2; 2024-03-08: 2; 2024-03-09: 2; 2024-03-10: 2
Complete/Upload Meeting Minutes One Document | Low Risk | Rhys | 100% | 2024-02-22 | 7
Complete/Upload Stakeholder Registry Documents | Med Risk | Artem | 100% | 2024-02-29 | 7
Create and upload 3 personas | Low Risk | Rhys, Terrence, Artem | 100% | 2024-03-04 | 7
Complete and upload progress report 1 | Milestone | Rhys, Terrence, Artem | 100% | 2024-02-28 | 1 | bar: 2024-02-28
Iteration 2
Finish Second Iteration | Goal | Rhys, Artem | 75% | 2024-03-12 | 17 | 2024-03-12: 2; 2024-03-13: 2; 2024-03-14: 2; 2024-03-15: 2; 2024-03-16: 2; 2024-03-17: 2; 2024-03-18: 2; 2024-03-19: 2; 2024-03-20: 2; 2024-03-21: 2; 2024-03-22: 2; 2024-03-23: 2; 2024-03-24: 2; 2024-03-25: 2; 2024-03-26: 2; 2024-03-27: 2; 2024-03-28: 2
Complete/Upload Meeting Minutes Two Document | Low Risk | Rhys | 100% | 2024-03-14 | 7
Complete/Upload Resource Needs Document | Med Risk | Rhys, Artem | 75% | 2024-03-19 | 7
Complete/Upload Gantt Chart | Med Risk | Artem | 100% | 2024-03-21 | 7
Update Github Boards (task list, readme) | Med Risk | Rhys, Artem | 100% | 2024-03-22 | 7
Complete/Upload Progress Report 2 | Milestone | Rhys, Artem | 100% | 2024-03-22 | 1 | bar: 2024-03-22
Iteration 3
Finish Third Iteration | Goal | Rhys, Artem | 0% | 2024-03-29 | 20 | 2024-03-29: 2; 2024-03-30: 2; 2024-03-31: 2; 2024-04-01: 2; 2024-04-02: 2; 2024-04-03: 2; 2024-04-04: 2; 2024-04-05: 2; 2024-04-06: 2; 2024-04-07: 2; 2024-04-08: 2; 2024-04-09: 2; 2024-04-10: 2; 2024-04-11: 2; 2024-04-12: 2; 2024-04-13: 2; 2024-04-14: 2; 2024-04-15: 2; 2024-04-16: 2; 2024-04-17: 2
Complete/Upload Meeting Minutes 3 Document | Low Risk | Rhys | 0% | 2024-04-01 | 7
Complete/Upload Risk Registry | High Risk | Rhys, Artem | 0% | 2024-04-06 | 7
Integrate Website and Publish | High Risk | Rhys, Artem | 0% | 2024-04-08 | 7
Complete/Upload User Testing Documents | Med Risk | Artem | 0% | 2024-04-10 | 7
Complete/Upload Progress Report 3 | Milestone | Rhys, Artem | 0% | 2024-04-10 | 1